## Sheet1
EECS 448 Project 4: Product Backlog
Feature/Name | Description | Estimated Effort | COMPLETION | Effort Scale
MECHANICS |  |  |  | Little = | < 2 hour
Left/Right Movement | User can move character left and right on the screen | Little | X | Moderate = | 3-4 hours
Jumping | User can make character jump. This portion includes editing the physics engine | Little | X | Heavy = | 4-7 hours
Enemy Characters | Enemies in the game that can harm the character and end the game | Moderate | X | Very Heavy = | Full Day
Weapon Usage | Weapon that player can use to defeat enemies | Moderate
Vertical Movement | Player can move up in the stage, in addition to maintaining side-to-side | Moderate | X
Enemy hitpoints | Enemies have a limited amount of HP that must be depleted before defeat | Moderate
Class System | Player can choose to modify their appearance/weapon choice | Very Heavy
Platforming | Player can jump from platform to platform | Little | X
Camera | Camera follows player throughout the course | Moderate | X
GRAPHICS
Blocky Graphics | Very basic graphics that the player first sees. Blocky, black and white | Little | X
8-Bit Graphics:
Background | Background of the stage, simple color pallette | Moderate
Player Sprites | 8-Bit sprite of the player, simple color pallette, animations included | Little
Enemy Sprites | 8-Bit sprites for the enemies, multiple frames for animation | Little
16-Bit Graphics:
Background | 16-bit stage background, more complex color pallette | Moderate
Player Sprites | 16-Bit sprites of the player, more complex color pallette, animations included | Little
Class-change sprites | 16-Bit sprites of the different classes the player can become, animations included | Heavy
Enemy Sprites | 16-Bit sprites for the enemies, multiple frames for animation | Moderate
Enemy Attack Sprites | Animations, visuals for more advanced enemy attacks (projectiles, etc.) | Moderate
Modern Graphics:
Background | Modern-looking background for stage, complex color pallette | Moderate
Player Sprites | Modern-looking player sprites, animations included | Little
Class-change sprites | Modern-looking player sprites for the class changes, animation included | Heavy
Enemy Sprites | Modern-looking enemy sprites, animation included | Moderate
Enemy Attack Sprites | Enemy attack animations for modern-graphics | Moderate
OTHER
Plot | Plot written to engage player in the game | Little
Title Screen/Entry Point | An entry point for when the player starts the game | Little